## Milestones and features
Milestone/Feature | RA Assigned | Order for development | Ready for Spec Review | Ready for internal Review
Milestone 612043/ Feature 644074 Load | Sandy | 1 | 2017-10-01
Milestone 612043/ Feature 615203 Unload | Sandy | 1 | 2017-10-01
Milestone 612043/ Feature 612753 Waste | Joy | 1 | 2017-11-01
Milestone 612043/ Feature 612707 Return | Joy | 1 | 2017-12-01
Milestone 612043/ Feature 660941 Waste during Return | Joy | 3 | 2017-12-01
Milestone 612043/ Feature 612706 Outdate | Joy | 2 | 2017-11-01
Milestone 612043/ Feature 612709 Inventory count | Joy | 2 | 2017-11-01
Milestone 612043/ Feature 612736 Receive | Sandy | 2
Milestone 612043/ Feature 612706 Med Stock Movement | Sandy | 2 | 2017-11-01
Milestone 612428 CSM: Dispensing and selling | Joy/Sandy | 3
Milestone 612428/ Feature 612700 Issue to Patient | Joy | 3
Milestone 612428/ Feature 612711 Fill a Prescription | Joy | 3
Milestone 612428/ Feature 612751 Issue to a Location | Joy | 3
Milestone 612428/ Feature 612756 Sell to another location | Joy | 3
Milestone 612428/ Feature 632859 Kits: Management and Use | Jennifer | 4
Milestone 612428/ Feature 660951 Issue Pending Loads | Joy | ?
Milestone 612428/ Feature 644089 MedStation AutoRestock | Joy | 5
Milestone 644796 CSM Compounding | Sandy | 4
Milestone 644796/ Feature 612730 Reverse Compounds | Sandy | 4
Milestone 644796/ Feature 612759 Manage standard compounds | Sandy | 4
Milestone 644796/ Feature 644807 Manage non-standard compounds | Sandy | 4
Milestone 612040 CSM: Mgmt of Expired CS Items/ Disposal (Destruction Bin) | Joy | 3
Milestone 612040/Feature 612696 Access destruction bin | Joy | 3 | 2017-11-01
Milestone 612040/Feature 660822 Adding Expired Items to Pending Destruction BIn | Joy | 3 | 2017-11-01
Milestone 612040/Feature 612692 Empty Destruction Bin | Joy | 3 | 2017-11-01
Milestone 215560 (ES) Be able to refill an ADM with items destocked from another ADM with close loop tracking (US and OUS) | Sandy | ?
Milestone 401105 (ES) Return Bin: Adding items when emptying a return bin (related to CM tracking) | Sandy | ?
Milestone 519034 (ES) Transaction slip: Remove - include patient DOB and route for controlled subs reporting (US, OUS) | Joy | ?
Milestone 612043 CSM: Inventory management capabilities (CSM) | Joy/Sandy | 2
Milestone 612043/ Feature 660868 Scheduling Cycle count | Joy | 3
Milestone 612043/ Feature 663587 Receive with PHG integration | Sandy | 3
Milestone 612043/ Feature 664473 Update/Edit barcode during Load | Sandy | 5
Milestone 612043/ Feature 664475 Update/Edit barcode during Receive | Sandy | 5
Milestone 612043/ Feature 664574 Barcode Management in CSM | Sandy | 5
Milestone 612046 CSM: Discrepancy resolution | Sandy | 4 | 2017-11-01
Milestone 612046/ Feature 612720 Resolve discrepancies | Sandy | 4 | 2017-11-01
Milestone 612046/ Feature 612723 Count Discrepancy Resolution | Sandy | 4 | 2017-11-01
Milestone 612046/ Feature 644079 View discrepancies and add resolution notes at ES server | Sandy | 4 | 2017-11-01
Milestone 612048 CSM: CS infrastructure support | Jonaid | 1
Milestone 612048/ Feature 612738 Messaging between facilities on same server | Jonaid | 2
Milestone 612048/ Feature 644105 CSM deployment flag for facilities | Jonaid | 2
Milestone 612048/ Feature 647670 CiiSafe db utility tool to support v8.x | Jonaid | 5
Milestone 612049 CSM: Streamlined investigational reporting | Jennifer | 5
Milestone 612049/ Feature 612758 All Discrepancies Report | Jennifer | 5
Milestone 612049/ Feature 612769 Compare Report | Jennifer | 5
Milestone 612049/ Feature 615193 Failed Access Report | Jennifer | 5
Milestone 612049/ Feature 617721 Outstanding Sheets | Jennifer | 5
Milestone 612050 CSM: Develop regulatory reporting | Jennifer | 5
Milestone 612050/ Feature 612794 All Activities Report | Jennifer | 5
Milestone 612050/ Feature 615175 All Users Report | Jennifer | 5
Milestone 612051 CSM: Report framework functionality | Jennifer | 5
Milestone 612051/ Feature 646137 Allow users to rearrange columns | Jennifer | ?
Milestone 612405 CSM: Inventory management reporting | Jennifer | 5
Milestone 612405/ Feature 615154 Refill Report (MedStation Auto Restock) | Jennifer | 5
Milestone 612405/ Feature 615155 Suggested Purchase Order Report | Jennifer | 5
Milestone 612405/ Feature 615164 Formulary Report | Jennifer | 5
Milestone 612405/ Feature 615165 Current Inventory Report | Jennifer | 5
Milestone 612405/ Feature 615167 Meds Pending Destruction Report | Jennifer | 5
Milestone 612405/ Feature 615190 Locations Report (may not be needed for MVP) | Jennifer | 5
Milestone 612405/ Feature 615210 Outdate Report | Jennifer | 5
Milestone 612405/ Feature 629169 Compounding Report | Jennifer | 5
Milestone 612405/ Feature 629170 Kit Report | Jennifer | 5
Milestone 612407 CSM: Interface with external and internal systems | Jonaid | 4
Milestone 612407/ Feature 646182 Interface - ordering, inventory, PAR | Jonaid | 4
Milestone 612407/ Feature 646184 Interface - restock | Jonaid | 4
Milestone 612407/ Feature 646205 Interface: CardinalAssist | Jonaid | 4
Milestone 612407/ Feature 646209 Interface: ADT | Jonaid | 4
Milestone 612407/ Feature 648964 Interface: Pyxis Check | Jonaid | 4
Milestone 612407/ Feature 649960 Interface: Sending transactions outbound - TECHNICAL | Jonaid | 4
Milestone 612407/ Feature 653071 Interface - MMS product updates | Jonaid | 4
Milestone 612413/ Feature 647890 CSM software storage space configuration | Joy | 1 | 2017-10-01
Milestone 612413 CSM: Hardware support | Joy | ? | 2017-10-01
Milestone 612424 CSM: ES User Management CSM support | Jonaid | 3
Milestone 612424/ Feature 612745 Create new permissions | Jonaid | 3
Milestone 612424/ Feature 644100 Support CSM report permissions | Jonaid | 3
Milestone 612424/ Feature 644106 CFN support user privilege definition | Jonaid | 3
Milestone 615158 CSM: Sheets/Labels | Jennifer | 6
Milestone 615158/ Feature 612691 Single and Multiple Med Sheets | Jennifer | 6
Milestone 615158/ Feature 612714 Labels | Jennifer | 6
Milestone 615158/ Feature 615137 Anesthesia Sheets | Jennifer | 6
Milestone 615158/ Feature 633733 Delivery Signature Sheet | Jennifer | 6
Milestone 615158/ Feature 640074 Reconciliation of Sheets | Jennifer | 6
Milestone 615158/ Feature 640086 Receipts | Jennifer | 6
Milestone 615158/ Feature 644132 Configurable auto reconcile setting for sheets | Jennifer | 6
Milestone 615158/ Feature 651898 Drip Sheets | Jennifer | 6
Milestone 632783 CSM: ES formulary CSM support | Jonaid | ?
Milestone 632783/Feature 612744 CSM specific formulary settings | Jonaid | 3
Milestone 215560/ Feature 644136 CSM- Scan MedStation transaction slip barcodes at CSM | Sandy | ?
Milestone 633111 CSM Barcode Scanning Workflows in CSM | Sandy | 3
Milestone 633111/ Feature 644136 CSM- Scan MedStation transaction slip barcodes at CSM | Sandy | ?
Milestone 633111/ Feature 644138 Support scanning for meds | Sandy | 3
Milestone 633111/ Feature 644139 Support scanning for labels | Sandy | 3
Milestone 633111/ Feature 644140 Support scanning for sheets | Sandy | 3
Milestone 633114 (ES) Station transaction slip changes | Sandy | ?
Milestone 633115 CSM: PLACEHOLDER for ES milestones to support CSM | Joy/Sandy | ?
Milestone 644080 CSM: Station Reports | Jennifer | 6
Milestone 644080/ Feature 644082 All Discrepancies Report (Station) | Jennifer | 6
Milestone 644080/ Feature 644083 Inventory Report (Station) | Jennifer | 6
Milestone 644080/ Feature 644084 Compare Report (Station) | Jennifer | 6
Milestone 644080/ Feature 644086 All Device Activities (Station) | Jennifer | 6
Milestone 644080/ Feature 644088 Allow station reports to print to a network printer | Jennifer | 6
Milestone 644796/ Feature 615131 Bulk to Unit Dose (Repackaging) | Sandy | 4
Milestone 647784 OUS: (ES) Ability to capture reference num during inventory workflows for controlled subs reporting | Joy | ?
Milestone 647784/ Feature 701156 When configured, Inventory Reference Number will be mandatory for specific Inventory Functions | Joy | ?
Milestone 647784/ Feature 701162 Server will require new Facility Formulary Management field: Require Inventory Reference Number | Joy | ?
Milestone 647784/ Feature 701168 MedStation requires new Inventory Reference Number Attribute | Joy | ?
Milestone 662398 CSM: Support like-for-like CiiSafe configuration | Joy | 1
| Sandy/ Jonaid | 1 Main screen, 1 Login | 2017-10-01
| Joy | 3 witness | 2017-11-01